## Sheet1
2022 State Employee Charitable Campaign Timeline
Date | Activity | By
2022-01-01 | New Year's Day (State offices closed)
2022-01-10 | Application announcement is posted by State Campaign Manager for statewide charities interested in participating in the SECC. | LCM
2022-01-17 | Martin Luther King, Jr. Day (State offices closed)
2022-01-21 | 2022 SECC Online Application Training for Statewide Charity Federations | STATEWIDE CHARITIES
2022-01-24 | Deadline for 2022 Local Campaign Manager applications and proposed budgets to be sent to Local Employee Committee Chair | LCM
2022-01-24 | Deadline for Local Campaign Managers to submit final 2021 campaign results report to State Campaign Manager, including list of leadership level donors | LCM
Week of January 24th | LEC MEETINGS: Review 2022 Local Campaign Manager applications, budget, and nominate LEC Chair | LEC
2022-01-27 | SAC MEETING: Review proposed SCM campaign plan, timeline, and budget | SAC
2022-01-28 | Begin distribution of SECC 2021 campaign funds | LCM
2022-02-01 | SPC MEETING: Review SAC recommendation of SCM campaign plan, timeline, budget, and determine the SCM. | SPC
2022-02-01 | 2022 SECC Local Charity Online Application Training for Local Campaign Managers | LCM
2022-02-04 | Statutory deadline for State Campaign Manager to submit final statewide campaign results reporting to Comptroller, SPC, and SAC | SCM
2022-02-07 | Deadline for Local Campaign Managers to send any requests to produce local campaign materials and/or incentive items to State Campaign Manager | LCM
2022-02-10 | LEC Chair sends recommended 2022 Local Campaign Manager, budget, and 2022 Local Employee Committee roster, including Chair to the SPC for approval | LEC
2022-02-14 | Application announcement is posted by Local Campaign Managers for local charities interested in participating in the SECC. | LCM
2022-02-21 | Presidents' Day (State offices closed)
2022-02-22 | Application deadline for charities applying as Statewide SECC charities, including 25-word descriptions and contribution impact information | STATEWIDE CHARITIES
February 23 - March 11, 2022 | State Campaign Manager conducts administrative review of Statewide charity applications | SCM
2022-02-23 | SECC Workshop & Roundtable webinar for all SECC stakeholders. Note: The 2022 Roundtable will be a virtual event. | ALL
2022-02-24 | SPC MEETING: Miscellaneous topics, 2022 SECC application review training, and approval of local region names and boundaries. | SPC
2022-02-25 | Deadline for SPC to submit 2022 SECC region names, boundaries, and LCM contact list to CPA | SCM
2022-03-02 | Texas Independence Day (Skeleton crew required at state offices)
2022-03-03 | SCM distributes contact list of LCMs approved for campaign year | SCM
2022-03-10 | Deadline for State Campaign Manager to alert statewide charity federations of application review findings | SCM
2022-03-11 | State Campaign Manager distributes statewide charity applications to State Policy Committee for eligibility review | SCM
March 11 - April 14, 2022 | State Policy Committee reviews statewide charity applications | SPC
2022-03-14 | Application corrections due from Statewide charity federations | STATEWIDE CHARITIES
2022-03-21 | SAC MEETING: Review proposed 2022 LCM budget and campaign materials | SAC
2022-03-23 | SPC MEETING: Approval of organizations serving as 2022 LCMs, LCM budgets,LECs, statewide campaign materials and theme(s), and any requests for locally-produced materials. | SPC
March 25 - April 15, 2022 | Local Campaign Managers conduct administrative review of local charity applications | LCM
2022-03-25 | Application deadline for charities applying as local SECC charities, including 25-word descriptions and contribution impact information | LOCAL CHARITIES
2022-03-29 | First distribution of funds to be finalized | LCM
2022-03-30 | Cesar Chavez Day (Optional state holiday)
2022-04-01 | Good Friday (Optional state holiday)
2022-04-14 | SPC MEETING: Determination of statewide charity eligibility | SPC
2022-04-14 | Deadline for Local Campaign Managers to alert local charities of application review findings | LCM
2022-04-14 | SCM notifies SWFs of eligibility decisions by SPC | SCM
2022-04-18 | Draft of directory distributed to Statewide charity federations for review/approval of charity listing information | SCM
2022-04-21 | San Jacinto Day (Skeleton crew required at state offices)
2022-04-22 | Deadline for corrections to local charities' application deficiencies noted in administrative review results notification | LOCAL CHARITIES
2022-04-25 | Directory charity listing alterations/approval due from SWFs | STATEWIDE CHARITIES
April 25 - May 2, 2022 | Local Employee Committees review local charity applications | LEC
2022-04-29 | SWF eligibility appeals due to SCM | SWF
2022-05-02 | State Campaign Manager distributes statewide charity application appeals to State Policy Committee for eligibility review | SCM
2022-05-02 | SECC Honorary Chair(s) request letters sent to: Governor, Lt. Governor, and Speaker of the House | SCM
2022-05-02 | Campaign incentive options made available to LCMs | SCM
Week of May 2nd | LEC MEETINGS: LECs meet to determine eligibility for all local 2022 SECC applicants and discuss materials/incentive items ordering | LEC
May 2 - 20, 2022 | State Policy Committee reviews statewide charity application appeals | SPC
2022-05-09 | Deadline for LCMs to send approval/denial letters to Local applicants (reasons for denial detailed) | LCM
2022-05-10 | List of approved/denied Local Organizations due to SCM | LCM
2022-05-16 | Local eligibility appeals due to SCM | LOCAL CHARITIES
May 16 - 20, 2022 | State Policy Committee reviews local charity application appeals | SPC
2022-05-17 | Deadline for ordering printed campaign materials and campaign incentive items through centralized ordering | LCM
2022-05-19 | SPC MEETING: Review statewide and local charity eligibility appeals (final eligibility results used to compile state section of SECC directory) and campaign planning. | SPC
2022-05-26 | Final list of all approved charities due to campaign materials | SCM
2022-05-27 | Routing of local campaign material proofs to LCMs begins | SCM
2022-05-30 | Memorial Day (State offices closed)
2022-06-10 | All centralized ordering printed campaign materials sent to printers | SCM
2022-06-16 | SPC MEETING (optional): Campaign planning and miscellaneous topics as needed. | SPC
2022-06-19 | Emancipation Day (Skeleton crew required at state offices)
2022-06-28 | Second distribution of SECC funds to be finalized | LCM
July 1 - 30, 2022 | SCM-provided online giving software training for all Local Campaign Managers | LCM
2022-07-04 | Independence Day
2022-07-21 | SPC MEETING (optional): Campaign planning and miscellaneous topics as needed | SPC
August 1 - 31, 2022 | Employee campaign coordinator trainings in all local regions | LCM
2022-08-01 | Campaign materials delivered to Local Campaign Managers (centralized ordering) | LCM
2022-08-18 | SPC MEETING: Campaign planning and miscellaneous topics | SPC
2022-08-26 | LBJ Day (Skeleton crew required at state offices)
September 1 - October 31, 2022 | Annual State Employee Charitable Campaign (statutorily authorized time to ask state or higher education employees for a charitable payroll deduction) | ALL
2022-09-05 | Labor Day (Offices closed)
2022-09-06 | Rosh Hashanah (Optional state holiday)
2022-09-08 | SPC MEETING: Campaign items and miscellaneous topics as needed | SPC
2022-09-29 | Third distribution of SECC funds to be finalized | LCM
2022-10-04 | Yom Kippur (Optional state holiday)
2022-10-20 | SPC MEETING: Campaign progress and miscellaneous topics | SPC
2022-10-28 | Final campaign result/report template due to LCMs | SCM
2022-11-03 | SPC MEETING: Approval of charity, SCM, and LCM applications for the next campaign year | SPC
2022-11-04 | Deadline for all online agencies to turn in all paper payroll deduction forms to their Local Campaign Manager for data entry into online software | LCM
2022-11-04 | Deadline for all non-online agencies to turn in all paper payroll deduction forms to their respective payroll offices for data entry | LCM
2022-11-10 | Veterans Day (State offices closed)
2022-11-11 | Payroll deduction forms due in state payroll offices | ECC
2022-11-16 | Deadline for Local Campaign Managers to enter all paper payroll pledges (only for all online agencies).
2022-11-24 | Thanksgiving Day (State offices closed)
2022-11-25 | Day After Thanksgiving (State offices closed)
December 1, 2022 - January 21, 2023 | Prepare final campaign results reporting for SCM | LCM
2022-12-07 | Application announcement is posted by current LCMs for charities interested in serving as a 2023 Local Campaign Manager | LCM
2022-12-14 | Request is posted for applications from charities interested in participating in the SECC as statewide federations or members. Note: 2023 is a re-certification application year for all qualifying federations and affiliate charitable organizations. | SCM
2022-12-24 | Christmas Eve Day (State offices closed)
2022-12-25 | Christmas Day (State offices closed)
2022-12-30 | Final distribution of SECC funds | LCM
2023-01-01 | New Year's Day (State offices closed)
2023-01-12 | SAC MEETING: Review proposed SCM campaign plan, timeline, and budget | SAC
2023-01-16 | Martin Luther King, Jr. Day (State offices closed)
2023-01-19 | SPC MEETING: Review SAC recommendation of SCM campaign plan, timeline, budget, and determine SCM | SPC
2023-01-20 | Deadline for Local Campaign Managers to submit final 2022 campaign results report to State Campaign Manager, including list of leadership level donors | LCM
2023-01-27 | Begin distribution of SECC 2022 campaign funds | LCM
* State Policy Committee and State Advisory Committee meeting dates and agenda subject to change
ECC | Employee Campaign Coordinator
LCM | Local Campaign Manager
LEC | Local Employee Committee
LOCAL CHARITIES | Local Charity Federations and Unaffiliated Charities
SAC | State Advisory Committee
SCM | State Campaign Manager
SPC | State Policy Committee
STATEWIDE CHARITIES | Statewide Charity Federation
Note on A16: gbennett: By law, the state campaign manager shall ensure that the state policy committee, the state advisory committee, and the comptroller receive the statewide campaign report not later than February 5th of the calendar year following the calendar year in which the campaign covered by the report ended. If February 5th is not a workday, then the first workday after February 5th is the deadline.