## Sheet1
2023 State Employee Charitable Campaign Timeline
Date | Activity | By
2023-01-01 | New Year's Day (State offices closed)
2023-01-09 | Application announcement is posted by State Campaign Manager for statewide charities interested in participating in the SECC. Note: 2023 is a re-certification application year for all qualifying federations and affiliate charitable organizations. | LCM
2023-01-16 | Martin Luther King, Jr. Day (State offices closed)
2023-01-19 | Confederate Heroes Day (Skeleton crew required)
2023-01-30 | Deadline for Local Campaign Managers to submit final 2022 campaign results report to State Campaign Manager, including list of leadership level donors | LCM
2023-01-31 | Distribution of SECC 2022 cash-check-credit or debit campaign funds | LCM
2023-02-03 | Deadline for 2023 Local Campaign Manager applications and proposed budgets to be sent to Local Employee Committee Chair | LCM
Week of February 6th | LEC MEETINGS: Review 2023 Local Campaign Manager applications, budget, and nominate LEC Chair | LEC
2023-02-06 | Statutory deadline for State Campaign Manager to submit final statewide campaign results reporting to Comptroller, SPC, and SAC | SCM
2023-02-09 | SAC MEETING: Review proposed SCM campaign plan, timeline, and budget, including local budgets | SAC
2023-02-10 | LEC Chair sends recommended 2023 Local Campaign Manager, budget, and 2023 Local Employee Committee roster, including Chair to the SPC for approval | LEC
2023-02-13 | Application announcement is posted by Local Campaign Managers for local charities interested in participating in the SECC. | LCM, LOCAL CHARITIES
2023-02-14 | Conference call for 2023 Local Campaign Managers - local charity application training and annual campaign planning | SCM, LCM
2023-02-16 | SPC MEETING: Review SAC recommendation of SCM campaign plan, timeline, budget, and determine the SCM; | SPC
2023-02-20 | Presidents' Day (State offices closed)
2023-02-21 | Conference call for local charity application training | SCM, LOCAL CHARITIES
2023-02-22 | Application deadline for charities applying as Statewide SECC charities, including 25-word descriptions and contribution impact information | STATEWIDE CHARITIES
2023-02-22 | Statewide training conference call led by Statewide Campaign Manager for current and prospective Local Employee Committee members | SCM, LEC, LCM
2023-03-02 | Texas Independence Day (Skeleton crew required at state offices)
2023-03-03 | SCM distributes contact list of LCMs approved for campaign year | SCM
March 6 - March 17, 2023 | State Campaign Manager conducts administrative review of Statewide charity applications | SCM
2023-03-20 | State Campaign Manager opens statewide charity applications to State Policy Committee for eligibility review | SCM
2023-03-20 | SECC Workshop & Roundtable webinar for all SECC stakeholders | ALL
2023-03-21 | Deadline for Local Campaign Managers to send any requests to produce local campaign materials to State Campaign Manager | LCM
2023-03-22 | SPC MEETING: Review and approve 2023 local region names and boundaries; 2023 SECC application review training; miscellaneous topics | SPC
2023-03-24 | Deadline for SPC to submit 2023 SECC region names, boundaries, and LCM contact list to CPA | SCM
2023-03-24 | Application deadline for charities applying as local SECC charities, including 25-word descriptions and contribution impact information | LOCAL CHARITIES
2023-03-27 | State Campaign Manager notifies statewide charity federations of application review findings | SCM
March 27 - April 14, 2023 | Local Campaign Managers conduct administrative review of local charity applications | LCM
March 27 - April 20, 2023 | State Policy Committee reviews statewide charity applications | SPC
2023-03-31 | First distribution of 2022 SECC funds to be finalized; LCMs will include donor designation and release of information with first distribution. LCMs will also share cross-region designation information with other LCMs. | LCM
2023-03-31 | Cesar Chavez Day (Optional state holiday)
2023-04-03 | Application corrections due from Statewide charity federations | STATEWIDE CHARITIES
2023-04-03 | SECC Honorary Chair(s) request letters sent to: Governor, Lt. Governor, and Speaker of the House | SCM
2023-04-07 | Good Friday (Optional state holiday)
2023-04-17 | Deadline for Local Campaign Managers to alert local charities of application review findings | LCM
2023-04-17 | Campaign incentive options made available to LCMs | SCM
2023-04-21 | San Jacinto Day (Skeleton crew required at state offices)
2023-04-24 | Draft of directory distributed to Statewide charity federations for review/approval of charity listing information | SCM
2023-04-24 | Deadline for corrections to local charities' applications | LOCAL CHARITIES
2023-04-24 | SAC MEETING: Review proposed 2023 campaign materials and theme | SAC
April 25 - May 1, 2023 | Local Employee Committees review local charity applications | LEC
2023-04-28 | SPC MEETING: Determination of statewide charity eligibility; review and approve 2023 LCMs and budgets; review and approve 2023 campaign materials, including any requests for locally produced materials; approve campaign theme(s); miscellaneous topics | SPC
2023-05-01 | SCM notifies SWFs of eligibility decisions by SPC | SCM
2023-05-01 | Directory charity listing alterations/approval due from SWFs | STATEWIDE CHARITIES
2023-05-01 | State Campaign Manager distributes statewide charity application appeals to State Policy Committee for eligibility review | SCM
May 1 - 17, 2023 | State Policy Committee reviews statewide charity application appeals | SPC
Week of May 1st | LEC MEETINGS: LECs meet to determine eligibility for all local 2023 SECC applicants and discuss materials/incentive items ordering | LEC
2023-05-05 | SWF eligibility appeals due to SCM | STATEWIDE CHARITIES
2023-05-08 | Deadline for LCMs to send approval/denial letters to Local applicants (reasons for denial detailed) | LCM
2023-05-15 | Local eligibility appeals due to SCM | LOCAL CHARITIES
2023-05-15 | List of approved/denied Local Organizations due to SCM | LCM
May 15 - 24, 2023 | State Policy Committee reviews local charity application appeals | SPC
2023-05-16 | Deadline for ordering printed campaign materials and campaign incentive items through centralized ordering | LCM
2023-05-24 | SPC MEETING: Review statewide and local charity eligibility appeals (final eligibility results used to compile state section of SECC directory) and campaign planning. | SPC
2023-05-25 | Final list of all approved charities due to campaign materials | SCM
2023-05-29 | Memorial Day (State offices closed)
2023-05-30 | Routing of local campaign material proofs to LCMs begins | SCM
2023-06-01 | Statewide conference call led by Statewide Campaign Manager for Higher Education representatives | SCM, LCM
2023-06-06 | All centralized ordering printed campaign materials sent to printers | SCM
2023-06-22 | SPC MEETING (optional): Campaign planning and miscellaneous topics as needed. | SPC
2023-06-19 | Emancipation Day (Skeleton crew required at state offices)
2023-06-30 | Second distribution of 2022 SECC funds to be finalized | LCM
July 1 - 30, 2023 | SCM-provided online giving software training for all Local Campaign Managers | SCM, LCM
2023-07-04 | Independence Day
2023-07-20 | SPC MEETING (optional): Campaign planning and miscellaneous topics as needed | SPC
August 1 - 31, 2023 | Employee campaign coordinator trainings in all local regions | LCM
2023-08-01 | Campaign materials delivered to Local Campaign Managers (centralized ordering) | SPC
2023-08-03 | Statewide online giving software training led by Statewide Campaign Manager, open to statewide campaign coordinators and local campaign coordinators from all regions | SCM
2023-08-10 | SPC MEETING & PLANNING RETREAT: Campaign planning and miscellaneous topics | SPC
2023-08-27 | LBJ Day (Skeleton crew required at state offices)
September 1 - October 31, 2023 | Annual State Employee Charitable Campaign (statutorily authorized time to ask state or higher education employees for a charitable payroll deduction) | ALL
2023-09-04 | Labor Day (Offices closed)
2023-09-07 | SPC MEETING: Campaign items and miscellaneous topics as needed | SPC
2023-09-15 | Rosh Hashanah (Optional state holiday)
2023-09-24 | Yom Kippur (Optional state holiday)
2023-09-29 | Third distribution of 2022 SECC funds to be finalized | LCM
2023-10-12 | SPC MEETING: Campaign items and miscellaneous topics as needed | SPC
2023-10-27 | Final campaign result/report template due to LCMs | SCM
2023-11-07 | Deadline for all online agencies to turn in all paper payroll deduction forms to their Local Campaign Manager for data entry into online software | LCM
2023-11-07 | Deadline for all non-online agencies to turn in all paper payroll deduction forms to their respective payroll offices for data entry | LCM
2023-11-09 | SPC MEETING: Approval of charity, SCM, and LCM applications for the next campaign year | SPC
2023-11-10 | Veterans Day (State offices closed)
2023-11-14 | Deadline for Local Campaign Managers to enter all paper payroll pledges (only for all online agencies). | LCM
2023-11-15 | Final payroll report due to CPA | SCM
2023-11-23 | Thanksgiving Day (State offices closed)
2023-11-24 | Day After Thanksgiving (State offices closed)
December 1, 2023 - January 22, 2024 | Prepare final campaign results reporting for SCM | LCM
2023-12-06 | Application announcement is posted by current LCMs for charities interested in serving as a 2024 Local Campaign Manager | LCM
2023-12-24 | Christmas Eve Day
2023-12-25 | Christmas Day (State offices closed)
2023-12-26 | Christmas holiday (State offices closed)
2023-12-29 | Final distribution of 2022 SECC funds | LCM
2024-01-01 | New Year's Day (State offices closed)
2024-01-08 | Request is posted for applications from charities interested in participating in the SECC as statewide federations or members. Note: 2024 is a re-certification application year for all qualifying federations and affiliate charitable organizations. | SCM
2024-01-15 | Martin Luther King, Jr. Day (State offices closed)
2024-01-18 | SAC MEETING: Review proposed 2024 SCM campaign plan, timeline, and budget | SAC
2024-01-22 | Deadline for Local Campaign Managers to submit final 2023 campaign results report to State Campaign Manager, including list of leadership level donors | LCM
2024-01-25 | SPC MEETING: Review SAC recommendation of SCM campaign plan, timeline, budget, and determine SCM | SPC
2024-01-26 | Begin distribution of SECC 2023 campaign funds | LCM
* State Policy Committee and State Advisory Committee meeting dates and agenda subject to change
ECC | Employee Campaign Coordinator
LCM | Local Campaign Manager
LEC | Local Employee Committee
LOCAL CHARITIES | Local Charity Federations and Unaffiliated Charities
SAC | State Advisory Committee
SCM | State Campaign Manager
SPC | State Policy Committee
STATEWIDE CHARITIES | Statewide Charity Federation
Note on A13: gbennett: By law, the state campaign manager shall ensure that the state policy committee, the state advisory committee, and the comptroller receive the statewide campaign report not later than February 5th of the calendar year following the calendar year in which the campaign covered by the report ended. If February 5th is not a workday, then the first workday after February 5th is the deadline.